## Sheet1
Perry Park Metro District
Five Year Firewise Plan
Draft 3-30-23
All parcels below requiring wildfire mitigation as listed as Priority 1 to 3 and are subject to change depending upon
grant funding, homeowner participation, climatic events, insect/disease or change in abutting uses.
Acronyms:
Res = abuts residential SFB = Shaded Fuel Break FB = Fire Break FDA = Future Development Area
HP = Highest Priority EEE = Emergency Egress Easement TBD = To Be Determined based on Development
| Grant Status |  | Grant Received
Grant Application in Progress
Wildfire Mitigation Project Areas
Priority | PPMD Parcel # | DC ID | Legal Description | Acres | Priority Code | Year Treated | Retreatment Required | Estimated Cost/acre | 2023 | 2024 | 2025 | 2026 | 2027 | Estimated Cost
1 | 32 | R0009161 | TRACT A PERRY PARK 7 12.475 AM/L | 12.475 | Res | 2011 | HP | 2800 | 34930 |  |  |  |  | 34930
1 | 24 | R0008192 | TRACT C PERRY PARK 2 16.07 AM/L | 16.07 | Res | 2011 | HP | 3500 |  | 56245 |  |  |  | 56245
1 | 25 | R0008213 | TRACT E PERRY PARK 2 2.029 AM/L | 2.029 | Res | 2011 | HP | 3500 | 7101.5 |  |  |  |  | 7101.5
1 | 26 | R0008221 | TRACT F PERRY PARK 2 1.446 AM/L | 1.446 | Res | 2015 | HP | 2800 | 4048.8 |  |  |  |  | 4048.8
1 | 27 | R0014373 | LOT 2 BLK 5 PERRY PARK 2 1.161 AM/L | 1.161 | Res | 2022 | 2025 | 350 |  |  | 406.35 |  |  | 406.35
1 | 28A | R0222527 | PT OF TRACT B PERRY PARK 2 PARCEL A-7-3 10.179 AM/L | 10.179 | SFB | 2022 | 2025 | 350 |  |  | 3562.65 |  |  | 3562.65
1 | 29 | R0008184 | TRACT A PERRY PARK 2 11.32 AM/L | 11.32 | Res | 2011 | HP | 3500 | 39620 |  |  |  |  | 39620
1 | 13 | R0008598 | TRACT G PERRY PARK 5 5.72 AM/L | 5.72 | Res | 2011 | 2024 | 2500 |  |  | 14300 |  |  | 14300
1 | 16 | R0009021 | TRACT D BLK 4 PERRY PARK 6 4.08 AM/L | 4.08 | Res | 2015 | 2024 | 1800 |  | 7344 |  |  |  | 7344
1 | 5 | R0008580 | TRACT F PERRY PARK 5 1.96 AM/L | 1.96 | Res | 2011 | 2024 | 1800 |  |  | 3528 |  |  | 3528
1 | 6 | R0008811 | TRACT A PERRY PARK 6 3.61 AM/L | 3.61 | Res | 2011 | 2024 | 1200 |  |  | 4332 |  |  | 4332
1 | 7 | R0008571 | TRACT E PERRY PARK 5 6.44 AM/L | 6.44 | Res | 2011 | 2024 | 1800 |  |  | 11592 |  |  | 11592
1 | 8 | R0008547 | TRACT B PERRY PARK 5 11.17 AM/L | 11.17 | SFB | 2022 | 2026 | 1200 |  |  |  | 13404 |  | 13404
1 | 9 | R0008555 | TRACT C PERRY PARK 5 0.786 AM/L | 0.786 | SFB | 2022 | 2026 | 350 |  |  |  | 275.1 |  | 275.1
1 | 10 | R0008563 | TRACT D PERRY PARK 5 0.444 AM/L | 0.444 | SFB | 2022 | 2026 | 350 |  |  |  | 155.4 |  | 155.4
1 | 11 | R0008601 | TRACT H PERRY PARK 5 3.45 AM/L | 3.45 | Res | 2011 | 2024 | 2800 |  |  | 9660 |  |  | 9660
1 | 12 | R0008619 | MOST OF TRACT J PERRY PARK 5 4.35 AM/L | 4.35 | SFB | 2022 | 2026 | 350 |  |  |  | 1522.5 |  | 1522.5
1 | 14 | R0004693 | TRACT B BLK 3 PERRY PARK 6 2.08 AM/L | 2.08 | Res | 2011 | 2026 | 1800 |  |  |  | 3744 |  | 3744
1 | 15 | R0009013 | TRACT C BLK 4 PERRY PARK 6 1.26 AM/L | 1.26 | Res | 2020 | 2024 | 350 |  | 441 |  |  |  | 441
1 | 17 | R0012642 | LOT 34 BLK 17 PERRY PARK 5 229-421 1.24 AM/L | 1.24 | Res | 2022 | 2027 | 350 |  |  |  | 434 |  | 434
1 | 18 | R0004685 | TRACT A PERRY PARK 5 59.27 AM/L ALL ACRES SUBJECT TO CE 9536469 | 59.27 | SFB | 2022 | 2025 | 200 |  |  | 11854 |  |  | 11854
2 | 21 | R0490903 | TRACT A PERRY PARK 3 & PART OF VACATED WACOUNDA CT PER 02067963 7.659 AM/L | 7.659 | SFB |  | 2026 | 1800 |  |  |  | 13786.2 |  | 13786.2
2 | 22 | R0009259 | TRACT C PERRY PARK 9 9.72 AM/L | 9.72 | SFB |  | 2026 | 1800 |  |  |  | 17496 |  | 17496
3 | 33 | R0008361 | TRACT A PERRY PARK 4 5.23 AM/L | 5.23 | FDA |  | TBD | 2500 | [5 empty] | 13075
3 | 34 | R0008379 | TRACT B PERRY PARK 4 6.21 AM/L | 6.21 | FDA |  | TBD | 2500 | [5 empty] | 15525
3 | 35 | R0008387 | TRACT C PERRY PARK 4 2.70 AM/L | 2.7 | FDA |  | TBD | 2500 | [5 empty] | 6750
3 | 36 | R0008395 | TRACT D PERRY PARK 4 4.17 AM/L | 4.17 | FDA |  | TBD | 2500 | [5 empty] | 10425
[8 empty] | Totals | 85700.3 | 64030 | 59235 | 50817.2 | 0 | 305557.5
Maintenance of Fuel Treatments
Evac Rtes: Public Safety- Treat every 2 years or annually as recommended by LFPD. | [8 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 |  |  | Country Club Drive (Completion) | 5 | EEE | 2022 | 2023 | 1200 | 6000 |  |  |  |  | 6000
|  |  | Country Club Drive (Maintenance) | 5 | EEE |  | 2025 | 350 |  |  | 1750 |  | 1750 | 3500
1 |  |  | Perry Park Blvd West |  | EEE
2 |  |  | Perry Park Blvd East |  | EEE
1 |  |  | Red Rock Drive |  | EEE
[8 empty] | Annual | 6000 | 0 | 1750 | 0 | 1750 | 9500
Fire Break: Fire Containment or Control. Every 3 years unless recommended sooner by LFPD. | [8 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 |  |  | Bannock Drive | 8 | FB | 2022 | 2025 | 350 |  |  | 2800 |  |  | 2800
1 |  |  | Cheyenne (Chippewa to Inca) | 4 | FB | 2022 | 2025 | 350 |  |  | 1400 |  |  | 1400
1 |  |  | Elati (Delaware to pavement) | 3 | FB | 2019 | 2024 | 350 |  | 1050 |  |  | 1050 | 2100
1 |  |  | Deleware (Quivas to pavement) | 1.5 | FB | 2022 | 2025 | 350 |  |  | 525 |  |  | 525
1 |  |  | Upper Cheyenne | 30 | FB | 2021 | 2024 | 350 |  |  |  | 10500 |  | 10500
[8 empty] | Annual | 0 | 1050 | 4725 | 10500 | 1050 | 17325
Shaded Fuel Breaks: Wildfire Behavior Modification. Every 3 years | [8 empty] | 2023 | 2024 | 2025 | 2026 | 2027
1 |  |  | Tract K | 25 | SFB | 2022 | 2026 | 350 |  |  |  | 8750 |  | 8750
1 |  |  | Greater Larkspur Proj. | 25 | SFB | 2023 | 2023 | N/A | 10000 |  |  |  |  | 10000
2 |  |  | Haystack Ranch | 30 | SFB | 2021 | 2024 | 350 |  |  | 10500 |  |  | 10500
2 |  |  | Turner Ranch | 10 | SFB | 2021 | 2024 | 350 |  |  | 3500 | 0 |  | 3500
[8 empty] | Annual | 10000 | 0 | 14000 | 8750 |  | 32750
Annual estimated budget for:
|  |  | Maintenance of fuel treatments | [5 empty] | 16000 | 1050 | 20475 | 19250 | 2800 | 59575
|  |  | Implementation of fuel treatments | [5 empty] | 85700.3 | 64030 | 59235 | 50817.2 | 0 | 305557.5
[8 empty] | Totals | 101700.3 | 65080 | 79710 | 70067.2 | 2800

## Sheet2
PPMD Properties, Other
The following parcels have been treated, or low priority or do not require mitigation
NOTE: Treated parcels will require re-treatement every 5 to 7 years to manage Gambel oak.
No Treatment Required
| Parcel # | DC ID | Legal Description | Acres |  | Description
| 1 | R0432633 | TRACT IN SW1/4NW1/4 25-9-68 LYING SOUTH OF RED ROCK DRIVE ACREAGE 1.969AM/L SUBJECT TO CONSERVATION EASEMENT 01032995 ACRES 9.672AM/L TOTAL ACREAGE 11.641AM/L | 11.641 |  | Gateway
| 2 | R0602729 | TRACT IN SW1/4NW1/4 25-9-68 LYING NORTH OF RED ROCK DR 8.043 AM/L 4.779 ACRES SUBJECT TO CE 01032995 2013021849 | 8.043 |  | Gateway
| 3 | R0602727 | TRACT IN E1/2SW1/4NW1/4 25-9-68 1.169 AM/L | 1.169 |  | Gateway
| 4 | R0004618 | A TRACT IN SW1/4 24 AND THE NW1/4 25-9-68 1 AKA VILLAGE INVESTORS PA REC 172405 3.645 AM/L SUBJECT TO CONSERVATION EASEMENT 01032995 42.955 AM/L TOTAL ACREAGE 46.60 AM/L | 46.6 |  | Gateway
| 19 | R0009241 | TRACT A PERRY PARK 9 8.52 AM/L | 8.52 |  | Wauconda Park, Riparian Area
| 20 | R0009195 | TRACT B PERRY PARK 9 2.28 AM/L | 2.28 |  | Grasslands
| 23 | R0008205 | TRACT D PERRY PARK 2 0.154 AM/L | 0.154 |  | Too small, treated by abutting owners
| 30 | R0359094 | AN ISLAND OF OPEN SPACE" BETWEEN LOTS 7 & 8 IN BLOCK 10 PERRY PARK #2 .22 AM/L" | 0.22 |  | Access Easement for abutting lot
| 31 | R0222615 | TRACT H PERRY PARK 2 0.237 AM/L | 0.109 |  | Rock Formation
Upper Cheyenne Parcels- Treated in 2022
Priority 3. Will require treatment in 5 to 7 years to manage Gambel oak with priority along Fire Breaks
| Parcel # | DC ID | Legal Description | Acres | Priority | Re-treatment Req'd | Cost/ac. | Est. Cost
| 37 | R0005768 | LOT 7 BLK 18 PERRY PARK 5 3.821 AM/L | 3.821 | 3 | Yes | 350 | 1337.35
| 38 | R0005750 | LOT 64 BLK 17 PERRY PARK 5 1.756 AM/L | 1.756 | 3 | Yes | 350 | 614.6
| 39 | R0005784 | LOT 7 BLK 19 PERRY PARK 5 0.93 AM/L | 0.93 | 3 | Yes | 350 | 325.5
| 40 | R0005792 | LOT 13 BLK 19 PERRY PARK 5 1.013 AM/L | 1.013 | 3 | Yes | 350 | 354.55
| 41 | R0005776 | LOT 37 BLK 18 PERRY PARK 5 0.945 AM/L | 0.945 | 3 | Yes | 350 | 330.75
| 42 | R0406452 | LOT 38 BLK 18 PERRY PARK #5 .976 AM/L REAL PORTION ON 0406450 | 0.976 | 3 | Yes | 350 | 341.6
| 43 | R0005805 | LOT 31 BLK 19 PERRY PARK 5 0.949 AM/L | 0.949 | 3 | Yes | 350 | 332.15
| 44 | R0008627 | TRACT L PERRY PARK 5 1.676 AM/L | 1.676 | 3 | Yes | 350 | 586.6
| 45 | R0005830 | LOT 4 BLK 23 PERRY PARK 5 0.949 AM/L | 0.949 | 3 | Yes | 350 | 332.15
| 46 | R0005813 | LOT 29 BLK 22 PERRY PARK 5 0.95 AM/L | 0.95 | 3 | Yes | 350 | 332.5
| 47 | R0005821 | LOT 38 BLK 22 PERRY PARK 5 0.917 AM/L | 0.917 | 3 | Yes | 350 | 320.95
| 48 | R0008150 | LOT 22 BLK 2 INDIAN HEAD 1 0.90 AM/L 312-350 | 0.9 | 3 | Yes | 350 | 315
| 49 | R0005856 | LOT 10 BLK 2 INDIAN HEAD 1 0.91 AM/L 312-350 | 0.91 | 3 | Yes | 350 | 318.5
| 50 | R0159521 | NW1/4NE1/4 28-9-68 202-267 PAT NO 05-70-0059 AKA A-10 NKA PARCEL A-5 TOTAL ACREAGE 40 AM/L | 40 | 3 | Steep Terrain > 50% slopes | 3500 | 140000
145842.2

## Sheet3
Parcels 1-18
Parcels 19-36
Parcels 37-50

## Sheet4
PPMD 5-year Firewise Plan Descriptions
This plan has been developed to aid the PPMD Board of Directors (Board) with planning and budgeting for wildfire mitigation expenditures as mandated by the 2004 Service Plan Amendment. All recommendations are based on its adopted 2023 Community Wildfire Protection Plan.
Semi-annual review should be conducted by the Firewise Committee (FWC) comprised of residents, natural resource managers and emergency service providers. Adjustments will be necessary depending on:
Grant opportunities
Climatic events
Forest insect or disease threats
Organized neighborhood mitigation projects encompassing multiple lots and PPMD open spaces
Priorities
The following priorities are based on potential wildfire threats to life, property and the natural resources of Perry Park. An attempt will be made to identify those requiring annual, periodic, or long-term treatment. For example, grass areas may be treated annually, Gambel oak areas treated every three years, or forested areas every 10-15 years.
Priority 1:
  Egress Routes- Fuels within 150 feet of traveled surface.
  Shaded Fuel Breaks (SFB)- Fuel treatment zones, minimum of 300 feet wide, intended to manage crown fire behavior.
    Connections to rock formations
    Connections to zones of low fuel volumes such as golf course, prairie fuels, bodies of water
    Properties outside of district boundaries abutting platted areas.
  Fire Breaks (FB)- Areas cleared of fuels to allow firefighters to safely halt wildfire spread by use direct attack, water, or prescribed fire (black lining or burning out of fuels).
    Undeveloped rights-of-way (ROW) within Perry Park ranging from 60 to 90 feet wide including any previously treated fuels 30 to 50 feet outside of the ROW.
  Open Spaces abutting existing residences- Treatment objective is “fire adaption” to:
    Modify wildfire behavior and/or fire intensity.
    Allow safe and effective access by firefighters to contain or control wildfire.
    Improve the effectiveness of aerial firefighting resources.
    Minimize damage/destruction to the forest resource.
    Allow quick recovery of native vegetation.
    Minimize post-fire erosion.
Dennis, F. C. (2011). Fuel Break Guidelines for Forested Subdivisions & Communities. Ft. Collins, Co: Colorado State Forest Service.